## NBCUX Lab
NBCUX LAB
| Purpose | Task | Resources | Hours | Rate | Cost | Duration (Weeks)
PHASE 1: STAKEHOLDER INTERVIEWS | Multiple rounds of interviews will help us step into the shoes of consumers, designers, and companies. These sessions will be documented and shared. Gaining insight into the domain of online shopping is crucial to understanding business goals and objectives. | Research & Interview Script Preparation | 1 person | 20 |  |  | 0.5
|  | Interviews, Recordings, and Documentation | 1 person | 10 |  |  | 0.25
|  | Interview Analysis | 1 person | 10 |  |  | 0.25
|  |  | 1 person | 40 hours |  |  | 1 week
PHASE 2: COMPETITIVE ANALYSIS | We want to identify key competitors and evaluate the strategies they use to determine their strengths and weaknesses. This data will allow us to develop a relative strategy that has distinctive advantages in the market. | Research | 1 person | 45 |  |  | 0.5
|  | Documentation | 1 person | 5 |  |  | 0.5
|  | Data Digestion & Synthesis | 2 people | 30 |  |  | 1
|  |  | 2 people | 80 hours |  |  | 2 weeks
PHASE 3: CONSUMER JOURNEY | We will envision all the different possible use cases and content options consumers may encounter. These maps will tell a story that represents what consumers need, want, and expect to help build a seamless experience. | Personas Development | 1 person | 15 |  |  | 0.5
|  | Scenario Development | 2 people | 35 |  |  | 1
|  | Storyboarding | 2 person | 25 |  |  | 0.5
|  | Consumer Journey Mapping | 3 people | 40 |  |  | 2
|  |  | 3 people | 120 hours |  |  | 3 weeks
PHASE 4: DESIGN & PERFORMANCE | Communicating a consistent product atmosphere is critical to us. How a product looks and how a product works is something near and dear to our heart. We not only want to entertain different choices for areas like typography and interactions, but we want to assess how our design serves to perform in the market. How easy is it to make a purchase? Is the interface increasing customer conversion rates? Ongoing optimization is necessary in order to reach the ultimate goal of creating a product that aligns with the wants and needs of our audience. | Design Guide Development | 1 person | 45 |  |  | 1
|  | Visual Design Exploration | 1 person | 35 |  |  | 1
|  | Performance Assessment | 2 people | 40 |  |  | 1
|  |  | 2 people | 120 hours |  |  | 3 weeks
PHASE 5: PROTOTYPE | A clickable prototype is exciting! Ideation sessions with retailers, television networks, and developers (i.e., Best Retail) will be carried out to help us define features that motivate sales performance. Afterwards, we will create a simulation that reflects these honed features in the prototype. | Ideation Sessions & Synthesis | 3 people | 15 |  |  | 1
|  | Visual Design & Production | 2 people | 40 |  |  | 0.5
|  | Wireframe Draft | 1 people | 30 |  |  | 0.5
|  | Prototype Coding & Development | 2 people | 75 |  |  | 2
|  |  | 3 people | 160 hours |  |  | 4 weeks
PHASE 6: USER TESTING | Not only do we want to catch consumers in the act, but we also want to run our prototype by our stakeholders. Together, they will provide us with highly comprehensive and contextual feedback that will give us the means to perfect the user experience. | Tester & User Script Development | 1 person | 15 |  |  | 1
|  | User Testing Session | 2 people | 25 |  |  | 1
|  | Synthesis of Results | 2 people | 80 |  |  | 1
|  |  | 2 people | 120 hours |  |  | 3 weeks
PHASE 7: ANNOTATED WIREFRAMES | A blueprint of the product will be created along with annotations mapping it to a content management system. This allows us to effectively communicate the functionality of the interface with developers and help them build the back-end system. | Final Wireframe Draft | 1 person | 25 |  |  | 0.5
|  | Wireframe Annotation | 1 person | 15 |  |  | 0.5
|  |  | 1 person | 40 hours |  |  | 1 weeks
PHASE 8: REQUIREMENTS LIST | We will work with key stakeholders to develop, grow, and define a concrete list of product specifications. | Stakeholder Meetings & List Development | 1 person | 10 |  |  | 0.5
|  | List Comparison | 1 person | 30 |  |  | 0.5
|  |  | 1 person | 40 hours |  |  | 1 weeks
PHASE 9: REFINEMENTS & REVISIONS | We care about our final products and we want to deliver the best user experience we can. | Revising & Refining | 3 people | 70 |  |  | 1.5
|  | Quality Assurance | 3 people | 10 |  |  | 0.5
|  |  | 3 people | 80 hours |  |  | 2 weeks
TOTAL |  |  | 3 people | 800 hours |  |  | 20 weeks